## Sheet1
Gantt Chart			13/03/2017	20/03/2017	27/03/2017	03/04/2017	10/04/2017	17/04/2017	24/04/2017	01/05/2017	08/05/2017	15/05/2017	22/05/2017	29/05/2017	05/06/2017	12/06/2017	19/06/2017	26/06/2017	03/07/2017	10/07/2017	17/07/2017	24/07/2017	31/07/2017	07/08/2017	14/08/2017	21/08/2017	28/08/2017	04/09/2017
			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
Start	13/03/2017	1	>
Security Threats	20/03/2017	2		>	-	-	-	-	-	-	-	-	X
Machine Learning Techniques	27/03/2017	3			-	-	-	-	-	-	-	-	X
Testing and Evaluation Methods	03/04/2017	4				-	-	-	-	-	-	-	-	X
Introduction	10/04/2017	5					>	er	X
Background	17/04/2017	6						-	-	X
Methodology & Aims and Objectives	24/04/2017	7							-	X
Ethics & Professional Considerations	01/05/2017	8								-	X
Evaluation and Finalising	08/05/2017	9									*
Identify Security Threats	15/05/2017	10										>	-	-	-	-	-	*
Investigate The Cause	22/05/2017	11											-	-	-	-	-	-	-	-	X
Review The Impact	29/05/2017	12												-	-	-	-	-	-	-	-	X
Outine The Solution	05/06/2017	13													-	-	-	-	-	-	-	-	*
Data Collection & Pre-Processing	12/06/2017	14														>	-	X
Extract Features	19/06/2017	15		Key													-	-	X
Train Machine Learning Model	26/06/2017	16		Start					>									-	-	X	*
Cross Validate The Model	03/07/2017	17		In Progress					-										>	-	-	X
Test Model	10/07/2017	18		Finish					X											-	-	-	X
Evaluate Model & Methodology	17/07/2017	19		Milestone					*												>	-	-	X
Evaluate Against Aims & Objectives	24/07/2017	20		Research																		-	-	-	X
Discuss areas for further work	31/07/2017	21		Project Plan and Overview																			-	-	-	X
Review & Finalise	07/08/2017	22		Analysis																				>	-	-	-
Review & Finalise	14/08/2017	23		Development																					-	-	-
Review & Finalise	21/08/2017	24		Testing																						-	-
Review & Finalise	28/08/2017	25		Evaluation																							X
Submit	04/09/2017	26																										*